## Summary
HORUS — CONSOLIDATED BETA TEST RESULTS
37 scenarios · 25 critical · 6 independent testers · 222 test reports · generated 2026-09-18
1 — RESULTS PER TESTER
Tester | OK | Partial | KO | Blocked | N/A | Not tested | Open defects | % OK (of tested)
Tester 1 | 26 | 3 | 4 | 1 | 3 | 0 | 8 | 76.47%
Tester 2 | 29 | 1 | 0 | 4 | 3 | 0 | 5 | 85.29%
Tester 3 | 28 | 1 | 5 | 0 | 3 | 0 | 6 | 82.35%
Tester 4 | 28 | 3 | 6 | 0 | 0 | 0 | 9 | 75.68%
Tester 5 | 19 | 2 | 13 | 0 | 3 | 0 | 15 | 55.88%
Tester 6 | 28 | 3 | 6 | 0 | 0 | 0 | 9 | 75.68%
ALL TESTERS | 158 | 13 | 34 | 5 | 12 | 0 | 52 | 0.75238
2 — SCENARIO CONSENSUS (what the testers agree on)
Verdict | Meaning | Scenarios | % of all | of which critical
Passed by all | Every tester who could run it reported OK. | 17 | 45.95% | 14
Mixed | Some testers OK, others Partial / KO / Blocked — reproduce before closing. | 18 | 48.65% | 10
Failed by all | Nobody got it working: Partial, KO or Blocked for every tester. | 2 | 5.405% | 1
Not covered | No tester could assess it (N/A or Not tested everywhere). | 0 | 0% | 0
3 — BY CATEGORY
Category | Scenarios | OK | Partial | KO | Blocked | N/A | Not tested | % OK (of tested)
Critical feature | 25 | 111 | 5 | 18 | 4 | 12 | 0 | 80.43%
User interface | 5 | 26 | 2 | 2 | 0 | 0 | 0 | 86.67%
Secondary function | 5 | 15 | 4 | 10 | 1 | 0 | 0 | 50%
Compatibility | 2 | 6 | 2 | 4 | 0 | 0 | 0 | 50%
4 — SCENARIOS RANKED BY NUMBER OF FAILING REPORTS
Feature ID | Feature Name | Category | Failing reports | Blocking | Major | Minor | Verdict | Testers who ran it
F13 | Search the documents | Critical feature | 6 | 1 | 4 | 0 | Failed by all | 6
F14 | List categories | Secondary function | 6 | 1 | 4 | 0 | Failed by all | 6
F27 | Receive a task result without refreshing | Critical feature | 4 | 0 | 2 | 0 | Mixed | 6
F28 | View the task list | Critical feature | 3 | 0 | 2 | 0 | Mixed | 6
F34 | Open the metrics page | Secondary function | 3 | 0 | 2 | 0 | Mixed | 6
F35 | Open the traces page and follow a request | Secondary function | 3 | 0 | 2 | 0 | Mixed | 6
F37 | Use the interface on a small screen | Compatibility | 3 | 0 | 2 | 0 | Mixed | 6
F26 | Route a task to a matching agent | Critical feature | 3 | 0 | 0 | 1 | Mixed | 6
F29 | Open a task's detail view | User interface | 3 | 0 | 0 | 1 | Mixed | 6
F30 | Cancel a task | Critical feature | 3 | 0 | 0 | 1 | Mixed | 6
F36 | Run the web client in different browsers | Compatibility | 3 | 0 | 0 | 2 | Mixed | 6
F15 | Delete a document | Critical feature | 2 | 1 | 1 | 0 | Mixed | 6
F25 | Create a task | Critical feature | 2 | 2 | 0 | 0 | Mixed | 6
F7 | Log out | Secondary function | 2 | 0 | 0 | 1 | Mixed | 6
F19 | Ask a complex question spanning several documents | Critical feature | 1 | 0 | 1 | 0 | Mixed | 2
F20 | Ask a question outside the corpus | Critical feature | 1 | 0 | 1 | 0 | Mixed | 2
F1 | Install and start Horus from the archive | Critical feature | 1 | 0 | 0 | 1 | Mixed | 6
F31 | Access the dashboard | Critical feature | 1 | 0 | 0 | 0 | Mixed | 6
F32 | Navigate with the command palette | User interface | 1 | 0 | 0 | 0 | Mixed | 6
F33 | Open the logs page | Secondary function | 1 | 0 | 0 | 0 | Mixed | 6

## Results
|  |  |  | CONSOLIDATED VERDICT | [7 empty] | TESTER 1 |  |  | TESTER 2 |  |  | TESTER 3 |  |  | TESTER 4 |  |  | TESTER 5 |  |  | TESTER 6 |  |  | SCENARIO SPECIFICATION
Feature ID | Feature Name | Category | Dev status (team) | Verdict | OK | Partial | KO | Blocked | N/A | Not tested | Worst severity | Result | Severity | Feedback / anomaly | Result | Severity | Feedback / anomaly | Result | Severity | Feedback / anomaly | Result | Severity | Feedback / anomaly | Result | Severity | Feedback / anomaly | Result | Severity | Feedback / anomaly | Objective | Prerequisites | Steps | Expected results
F1 | Install and start Horus from the archive | Critical feature | Done | Mixed | 5 | 1 |  |  |  |  | Minor | OK |  | I don't think that for a tester it should be installed that way and locally. It takes a lot of time, network bandwith, etc. To be completely honest, this kind of setup should NOT be done by the betatester, specially with the amount of resources required. A live demo in a VPS or similar should be provided. If it is helpful, here I provide the specs of my laptop: Host: TUXEDO InfinityBook Pro Gen8 (MK1) OS: Arch Linux x86_64 Kernel: 6.18.50-1-lts CPU: 13th Gen Intel Core i7-13700H, 20 threads, 3.5 GHz GPU: Intel Raptor Lake-P, Iris Xe Graphics Memory: 32 GB RAM | OK |  |  | OK |  |  | OK |  |  | Partial | Minor | Install took more than 2 hours total (readme says 10-30 min). It failed 2 times with docker hub timeouts when pulling multiple images at same time (redis, rabbitmq etc), but pulling them one by one worked fine so i think its a parallel download issue not my network. After that, build finished ok but exit code 42 happened because 'mas' container was marked unhealthy - checked mas logs myself and everything was actually fine, no errors, i think the healthcheck just needs more time on first boot. Because of that the installer stopped before starting web_client and agent, so localhost:3000 didnt work at first. Had to manually run 'docker compose up -d' again to get the rest of the containers up. After that i could reach the login screen fine. | OK |  |  | A tester installs Horus by extracting the archive and double-clicking one file, with no terminal, no clone and no manual editing, and ends up on the login screen | Docker Desktop installed AND RUNNING; Python 3.11+; free disk of 150 GB for a CPU install or 125 GB for GPU; Horus-Beta-0.1.0.zip downloaded from the OneDrive link on the Info & Access tab. The disk figures are measured build PEAKS. The install settles to about 130 GB (CPU) or 110 GB (GPU) afterwards. Download is about 25 GB. No NVIDIA GPU is required: the installer detects the hardware and selects a CPU profile itself. | 1. Extract the WHOLE archive to a folder 2. Read README-FIRST.txt (40 lines, plain text) 3. Run the launcher for your platform: Windows double-click START-HERE-Windows.bat; macOS right-click START-HERE-macOS.command and choose Open; Linux ./START-HERE-Linux.sh 4. Choose a file-access option when asked (option 1 uses the bundled sample documents), then confirm 5. Wait. The first run builds the images, then downloads the model weights. Allow 1.5-2 hours. The installer prints progress and is not frozen. Later starts take about 90 s. 6. When it reports success, open http://localhost:3000 in a browser | The installer runs its preflight checks (Python, Docker, Compose, free disk, network, ports), probes the hardware, chooses a profile, builds and starts the stack, and finishes with a 9-step smoke test. On failure it gives a distinct exit code and an actionable message, plus install-log.txt and horus-profile.json to send back. http://localhost:3000 shows the Horus login screen. With an NVIDIA GPU: 12 services are Up, 5 of them health-checked and healthy (mas, postgres, redis, rabbitmq, vllm). Without a GPU: the installer prints a warning up front, selects the CPU profile, and 11 services are Up with 4 healthy. The install still completes and reports success. Only F18, F19 and F20 are out of reach on a CPU install; record those as NOT APPLICABLE. vllm downloads its model last, so it is the last to go healthy. Allow extra time.
F2 | Open Horus as a desktop application | User interface | In progress | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | After installing, the tester opens an application window rather than being told to visit localhost:3000, and the application manages the stack for them | F1 passed | 1. Open the app: Windows app/Horus.exe / macOS app/Horus.app / Linux install app/Horus_0.1.0_amd64.deb then launch Horus 2. Accept the unsigned-binary warning (Windows: More info then Run anyway; macOS: right-click then Open, twice) 3. Watch the status screen while the stack starts 4. Use the Horus menu: Stop, Restart, Open install-log.txt, Open horus-profile.json 5. Close the window and answer the shutdown prompt | A native window titled Horus opens, with the Horus icon and no browser chrome. A status screen shows: the current step one row per service with its health elapsed time the raw Docker output on demand When the stack is ready the window is replaced by the Horus client loaded from http://localhost:3000, so the session token is preserved. Reachable from both the native menu and the status window: Stop, Restart, Open install-log.txt, Open horus-profile.json Closing asks whether to leave the stack running, and remembers the answer. localhost:3000 in a browser remains a supported fallback.
F3 | Sign in with the seeded administrator | Critical feature | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | Sign in with the administrator account that MAS creates automatically at startup. The tester does not create it. | F1 passed | 1. Go to http://localhost:3000/auth/login 2. Username: admin 3. Password: admin 4. Submit | Login succeeds and the dashboard loads with the Admin section visible. This account already exists: MAS seeds it at startup. Registering a new account never grants admin, whatever the creation order.
F4 | Manage users as an admin (view, create, change role, delete) | Critical feature | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | An admin sees every account, creates the team accounts, changes a role and sees it take effect at once, and removes an account so that it really loses access | Signed in as the seeded administrator (F3) | 1. Go to /admin/users. The table lists every account with its role; the search field and the role filter narrow it. 2. Click Create New User. Username horus.admin, password HorusATP2026!, role admin. Submit. 3. Repeat for horus.manager (manager), horus.user (user) and horus.user2 (user). 4. Click Edit User Role on horus.user2, select manager, save. 5. In a private window, log in as horus.user2 and open /tasks. 6. Back as admin, set horus.user2 to user again; in the private window, reload /tasks. 7. Create horus.disposable / HorusATP2026! with the user role, and log in as it in a second private window; leave that window open. 8. Back as admin, click Delete User on horus.disposable and confirm in the dialog. Reload the page. 9. Try to log in as horus.disposable again. In the window from step 7, reload /dashboard. | Steps 1-3: every account is listed with its username and role. New accounts appear immediately with the role chosen, and each can log in. Steps 4-6: as manager, horus.user2 can view the task queue; back as user, the manager-only actions are no longer available. No restart is needed. Steps 8-9: a confirmation dialog is shown first, then horus.disposable disappears from the table. Login is refused, and the still-open session can no longer load protected data.
F5 | Register a standard account | Critical feature | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | A newcomer can self-register, receives the default user role, and the password policy holds | F1 passed | 1. Go to /auth/register 2. First try the password horus (too short, no digit or symbol) 3. Then register horus.user / HorusATP2026! 4. Log in | The weak password is refused with a readable message: at least 10 characters with an uppercase, a lowercase, a digit and a special character. The same rule applies on the sign-up form, in the Admin > Users panel and on the MAS server, which returns a 422 the web client displays. The valid registration creates an account with the user role, and the Admin section is NOT visible for it.
F6 | Log in | Critical feature | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | Sign in with an existing account and reach the dashboard | An existing account | 1. Go to /auth/login 2. Enter username and password 3. Submit | Login succeeds within 2 s and the user lands on the dashboard.
F7 | Log out | Secondary function | Done | Mixed | 4 | 2 |  |  |  |  | Minor | Partial | Minor | Slight delay, if I click instant it restores an authenticated view, I managed to recreate it a couple of times. | OK |  |  | Partial |  |  | OK |  |  | OK |  |  | OK |  |  | End the session and invalidate the token | Stack running, tester logged in to the web client | 1. Click the account menu 2. Click Log out 3. Try to navigate back to /dashboard using the browser back button | The user returns to the login page and the back button does not restore an authenticated view.
F8 | Register an agent | Critical feature | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | An admin can add a specialised agent and receive its API key | Logged in as horus.admin | 1. Go to /admin/agents 2. Click Register New Agent 3. Name: FinCorp-Analyst 4. Description: Financial analyst agent 5. Skills: financial_analysis, compliance, reporting, document_qa 6. Submit 7. Copy the generated API key | The agent is created, an API key is returned exactly once and is displayed to the admin, and the agent appears in the registry.
F9 | View the agent registry | Critical feature | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | Any authenticated user can see which agents exist and whether they are up | F8 passed | 1. Go to /dashboard 2. Read the agents list 3. Repeat while logged in as horus.user | FinCorp-Analyst is listed with its skills and an online status, for the admin and for the standard user alike.
F10 | View agent details | User interface | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | See one agent's full record from the admin agents page | F8 passed; signed in as horus.admin | 1. Go to http://localhost:3000/admin/agents 2. Click FinCorp-Analyst in the list to open its details 3. Compare what is shown with the agent card on /dashboard | The detail view shows the agent's id, name, description, skills and current status, and it matches what the dashboard shows for the same agent.
F11 | Unregister an agent | Critical feature | Done | Passed by all | 6 | [6 empty] | OK |  | UI needs improvement - A lot of horizontal scroll. | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | An admin can remove an agent from the registry | F8 passed, logged in as horus.admin | 1. Go to /admin/agents 2. Unregister FinCorp-Analyst 3. Confirm 4. Reload /dashboard 5. Register FinCorp-Analyst again, so later scenarios still have it | The agent disappears from the registry and no new task is routed to it. After step 5 it is back and routable.
F12 | Upload documents | Critical feature | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | Load the company documents into the knowledge store and see them analysed automatically | 1. F1 passed, stack running 2. Tester logged in to the web client 3. The 5 corpus documents to hand: horus/demo_assets/ inside the extracted archive. No repository access is needed - they ship in the ZIP. Accepted file types: PDF, Markdown (.md), Excel (.xlsx), plain text and configuration files (for example .env), and images (.jpeg, .png). Most common formats are accepted. The five sample files are .md. | 1. Go to /knowledge-store 2. Click Upload Files 3. Select all 5 .md files from horus/demo_assets/ in the folder you extracted 4. Confirm the upload 5. Wait for processing to finish 6. Click each document to open its detail panel | All 5 documents are ingested, each in under 20 s. The document list shows every one of them with its category, and the Documents Stored and Storage Used tiles match the number uploaded. Without any manual tagging, each document's detail panel shows an auto-detected category (Finance, HR, Compliance, IT), a short summary, and extracted entities: people, amounts and dates. The expected category and entities per file are listed on the Info & Access tab under Test corpus.
F13 | Search the documents | Critical feature | Done | Failed by all |  |  | 5 | 1 |  |  | Blocking | KO | Major | Didnt work - Simply nothing happened. Maybe I am blind but i didnt find the filters either. | Blocked | Blocking | It never loads | KO | Major | Nothing happened, doesnt work | KO | Major | No result come back | KO |  | There is no search field inside the knowledge-store page itself, only the global nav search bar at top which just suggests pages to go to (Dashboard, Chat, Knowledge Store), it doesnt search inside documents at all. Also i dont see any category filter anywhere on this page, just a static table with Document/Category/Summary/Date/Size/Details columns. Tried clicking around (the icons next to the bell, the Category column header) but found nothing | KO | Major | No result come back | Find relevant excerpts by typing a query, then narrow them by category | F12 passed | 1. On /knowledge-store, type Q4 revenue in the search field 2. Apply the category filter Finance | Results come back in under 3 s, ranked, with a readable text excerpt per hit. The category filter removes non-Finance documents.
F14 | List categories | Secondary function | Done | Failed by all |  |  | 5 | 1 |  |  | Blocking | KO | Major | Did not find filtres. | Blocked | Blocking | It never loads | KO | Major | The same, couldnt find the filters | KO | Major | No catecory filter | KO |  | Cant test this because there is no category filter UI anywhere on the knowledge-store page (same issue as F13). The categories are only visible as plain text in the table column, no dropdown/filter to open and compare against. | KO | Major | No category filter | See the categories the pipeline assigned on its own, as offered in the knowledge store's filter | F12 passed | 1. On /knowledge-store, open the category filter 2. Compare the list it offers with the category shown on each document in the list | The filter offers exactly the categories that were assigned to the uploaded documents, with no duplicates and no empty entries.
F15 | Delete a document | Critical feature | Done | Mixed | 4 |  | 1 | 1 |  |  | Blocking | Blocked | Blocking | Search did not work previously. | OK |  |  | KO | Major | Didnt worked the seaarch | OK |  |  | OK |  |  | OK |  |  | A user can remove a document, and the removal reaches search and chat, not only the list | F12 passed | 1. Go to /knowledge-store 2. Delete 5_IT_Security_Policy.md 3. Confirm 4. Reload the page 5. Search the corpus for a phrase that only existed in that document 6. Ask the same thing in a chat conversation | Steps 1-4: the document leaves the list and the Total Documents counter drops by one. Steps 5-6: no excerpt from the deleted document is returned and the agent no longer cites it. No phantom results.
F16 | Create a conversation | Critical feature | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | A user can open a new named conversation | Stack running, tester logged in to the web client | 1. Go to /conversations 2. Click New conversation 3. Name it ATP-Test-01 4. Confirm | The conversation is created and appears at the top of the list straight away.
F17 | Send a message | Critical feature | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | A user can post a message inside a conversation | F16 passed; at least one agent registered (F8) | 1. Open the conversation 2. Type: What was our Q4 2025 revenue? 3. Press Enter | The message appears in the thread in under 1 s and is attributed to the sender.
F18 | Ask a question and receive a grounded answer | Critical feature | Done | Passed by all | 2 |  |  |  | 4 |  |  | N/A |  | CPU Only | N/A |  | We don't have a GPU | N/A |  |  | OK |  |  | N/A |  |  | OK |  |  | Ask one factual question and wait for an answer drawn from the uploaded documents, with its source named | GPU REQUIRED. On a CPU-only machine the answer does arrive - about 1-2 min on a 12-core machine, up to about 7 min on 4 cores - but digits are corrupted in the output, so the accuracy target cannot be met. A CPU tester records this as NOT APPLICABLE, not failed. F12 passed (corpus uploaded); an agent is online | 1. In a conversation, ask: What was our Q4 2025 revenue? 2. Wait for the answer | GPU REQUIRED - see Prerequisites. The answer arrives in under 15 s, identifies Q4 2025 revenue as $4.2M, and cites 1_Q4_2025_Financial_Report.md as its source. The figure may be returned on its own (for example '$4.2M'). That is acceptable as long as the source is named, either in the message or in the sources panel beside it. Answers are cached by exact question text, so a re-test needs different wording.
F19 | Ask a complex question spanning several documents | Critical feature | Done | Mixed | 1 |  | 1 |  | 4 |  | Major | N/A |  | CPU Only | N/A |  | We don't have a GPU | N/A |  |  | KO | Major | Bad reponse | N/A |  |  | OK |  |  | Ask one question that needs two documents and wait for an answer that uses both | GPU REQUIRED. On a CPU-only machine the answer does arrive - about 1-2 min on a 12-core machine, up to about 7 min on 4 cores - but digits are corrupted in the output, so the accuracy target cannot be met. A CPU tester records this as NOT APPLICABLE, not failed. F12 passed; an agent is online | 1. Ask: Compare our Q4 spend against what the expense policy allows and flag anything out of policy. 2. Wait for the answer | GPU REQUIRED - see Prerequisites. The answer arrives in under 60 s and cites BOTH 1_Q4_2025_Financial_Report.md and 4_Expense_Policy.md. It must show, in the answer text: the Q4 spend figures it used the matching threshold from the expense policy a stated conclusion on whether each item is within policy A bare yes or no, or an answer citing only one document, does not pass.
F20 | Ask a question outside the corpus | Critical feature | In progress | Mixed | 1 |  | 1 |  | 4 |  | Major | N/A |  | CPU Only | N/A |  | We don't have a GPU | N/A |  |  | OK |  |  | N/A |  |  | KO | Major | Response for user : The capital of Peru is Lima. | The agent must not invent an answer it cannot ground | GPU REQUIRED. On a CPU-only machine the answer does arrive - about 1-2 min on a 12-core machine, up to about 7 min on 4 cores - but digits are corrupted in the output, so the accuracy target cannot be met. A CPU tester records this as NOT APPLICABLE, not failed. F12 passed; an agent is online | 1. Ask a question with no answer in the corpus, e.g. What is the capital of Peru? | GPU REQUIRED - see Prerequisites. The agent states that the knowledge base contains nothing relevant instead of presenting an ungrounded answer as fact.
F21 | View message history | Critical feature | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | A conversation reopens with its full history in the right order | F17 passed; the conversation contains at least two messages | 1. Leave the conversation 2. Reload the page 3. Reopen the same conversation | Every message is restored in chronological order with the correct author.
F22 | List conversations | Critical feature | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | A user sees all of their own conversations | F16 passed (ATP-Test-01 exists) | 1. Go to /conversations 2. Create two more conversations, named ATP-Test-02 and General-Test 3. Reload the page | All three conversations (ATP-Test-01, ATP-Test-02, General-Test) are listed with their names, and the list survives a reload.
F23 | Search conversations | User interface | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | Find a conversation by name in a long list | F22 passed with several conversations | 1. On /conversations, type ATP in the search field | Only conversations whose name matches are shown; clearing the field restores the full list.
F24 | Delete a conversation | Critical feature | Done | Passed by all | 6 | [6 empty] | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | A user can remove a conversation they own; an admin or manager can remove any | F16 passed; horus.user, horus.admin and horus.manager accounts exist | 1. As horus.user on /conversations, delete ATP-Test-01 2. Confirm 3. Reload the page 4. Still as horus.user, create a conversation named ATP-Moderation 5. Log in as horus.admin and delete ATP-Moderation 6. As horus.user, create ATP-Moderation-2; log in as horus.manager and delete it | Steps 1-3: the conversation disappears from the list and its messages are gone with it. Steps 4-6: both the admin and the manager can delete a conversation they do not own, and the owner no longer sees it.
F25 | Create a task | Critical feature | Done | Mixed | 4 |  | 2 |  |  |  | Blocking | OK |  |  | OK |  |  | OK |  |  | KO | Blocking | Crash and "something went wrong" | OK |  |  | KO | Blocking | The /tasks/new page crashes before anything is submitted and shows the generic "Something went wrong" error page. Browser console shows: [@mantine/core] Duplicate options are not supported. Option with value "1_Q4_2025_Financial_Report.md" was provided more than once. Cause: the file-attachments picker on the page uses the document filename as the option key, and the knowledge store contained the same file twice (uploaded a second time during testing). The app should not crash when two documents share a filename. Task creation itself works: the same request sent to the backend API returns 200 and a task id. Workaround: delete one of the duplicate documents on /knowledge-store, after which the form renders and dispatches correctly. | A user can submit work with a demand and required skills | An agent is registered (F8); logged in | 1. Go to /tasks/new 2. Demand: Summarise the Q4 financial report 3. Required skills: financial_analysis, document_qa 4. Submit | The task is accepted, given an id, and appears with status pending then running.
F26 | Route a task to a matching agent | Critical feature | Done | Mixed | 3 | 2 |  | 1 |  |  | Minor | Partial | Minor | I should not have to research for the login credentials. | Blocked |  | Cannot login I dont now the username | OK |  |  | OK |  |  | Partial |  | My computer crashed/froze while i was testing this, right when i was about to submit the task. Not sure yet if it was something with horus itself using too much memory/cpu or just my pc being weak, need to check resource usage next time before retrying | OK |  |  | Tasks reach an agent whose skills actually match | F25 passed; at least two agents with different skills registered | 1. Register a second agent with unrelated skills 2. Create a task requiring financial_analysis 3. Follow the task to completion 4. Check the RabbitMQ UI at http://localhost:15672 | The task is routed to FinCorp-Analyst and not to the unrelated agent; the queue shows the message on the matching route.
F27 | Receive a task result without refreshing | Critical feature | Done | Mixed | 2 |  | 3 | 1 |  |  | Major | KO | Major | Task seems stuck. I waited ~10 minutes. | Blocked |  | Never finishes | KO | Major | I had to wait more than 5 minutes, something is not rgiht there | OK |  |  | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | OK |  |  | The result is pushed to the user without a manual refresh | F25 passed; the conversation view is open | 1. Submit a task 2. Leave the page open without refreshing 3. Wait for the agent to finish | A task-result notification arrives over the WebSocket and the UI updates on its own; the payload matches the detail page.
F28 | View the task list | Critical feature | Done | Mixed | 3 |  | 3 |  |  |  | Major | OK |  |  | OK |  |  | OK |  |  | KO | Major | The tiles and the table not add up. total tasks ashowed 10 while the recent task table listed 8 | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | KO | Major | The tiles and the table do not add up. Total Tasks showed 10 while the Recent tasks table listed 8. The Completed tile also counted 2 more than the table. Cause: the stats endpoint counts every task row including subtasks of decomposed tasks, while the list shows only root tasks. The two extra rows are the subtasks of the F19 multi-document question. | Browse the submitted tasks and see the state of the queue on the same page | F25 passed; several tasks submitted, at least one completed and one cancelled (F31) | 1. Go to /tasks 2. Read the Recent tasks table 3. Read the tiles above it: Pending, Running, Completed, Failed, Cancelled and Timeout, plus Total Tasks and Success Rate | The submitted tasks are listed with their status. The six state tiles and the two totals add up: Total Tasks equals the number of tasks listed, and each tile matches the count of tasks in that state in the table.
F29 | Open a task's detail view | User interface | Done | Mixed | 3 | 2 | 1 |  |  |  | Minor | OK |  |  | OK |  |  | OK |  |  | Partial |  | Skils are not there and the created /finished tiemestamps | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | Partial | Minor | The detail page shows the demand, assigned agent, status and the result. Missing: the required skills are not displayed anywhere, and there are no created/finished timestamps (only the time on the Message Flow entry). Cosmetic: the agent card keeps showing a loading spinner after the task is completed. | Inspect one task's full record | F25 passed | 1. On /tasks, click a task 2. Read its detail page | The page shows the demand, required skills, assigned agent, status, timestamps and the result when the task has finished.
F30 | Cancel a task | Critical feature | Done | Mixed | 3 | 2 | 1 |  |  |  | Minor | Partial | Minor | Took too long to load, closed my session. But ended up cancelling. | Partial |  |  | OK |  |  | OK |  |  | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | OK |  |  | An admin can stop a task that is pending or already running, from the task's own page | F25 passed; signed in as horus.admin | 1. On /tasks, submit a new task 2. While it is still pending or running, click it to open its page at /tasks/<task id> 3. Click Cancel and confirm 4. Go back to /tasks | The task moves to Cancelled within 5 s, the Cancelled counter on /tasks increases by one, and no result is produced for it afterwards.
F31 | Access the dashboard | Critical feature | Done | Mixed | 5 |  | 1 |  |  |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | OK |  |  | The landing view after login loads quickly and its analytics update live | Signed in; at least one agent registered (F8) | 1. Log in and land on /dashboard 2. Reload five times and note the load time each time 3. Watch the analytics graph for about 60 s 4. In a second tab, submit a task, and keep watching the graph | The dashboard renders in under 3 s on each of the five reloads, with the agents list and the analytics widget, and no error state. The graph refreshes about every 10 s, and the active agents, running tasks and pending tasks series move when the new task is submitted.
F32 | Navigate with the command palette | User interface | Done | Mixed | 5 |  | 1 |  |  |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | OK |  |  | Reach the main sections from the keyboard | Stack running, tester logged in to the web client | 1. Open the command palette from the navigation bar 2. Choose Go to Dashboard, then Open Chat, then Knowledge Store | Each entry navigates to the matching page without a full page reload.
F33 | Open the logs page | Secondary function | Done | Mixed | 5 |  | 1 |  |  |  |  | OK |  |  | OK |  |  | OK |  |  | OK |  |  | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | OK |  |  | Centralised logs are readable inside the product, without Grafana | Logged in as horus.admin; traffic generated by earlier scenarios | 1. Go to /admin/logs 2. Filter by service (mas, agent, knowledge-store) | Recent log lines from the selected service are shown and reflect the actions performed during this test run.
F34 | Open the metrics page | Secondary function | Done | Mixed | 3 |  | 3 |  |  |  | Major | KO | Major | There are no latency panels. | OK |  |  | KO | Major | Couldnt find the latency panels | OK |  |  | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | OK |  |  | Service metrics are readable inside the product | Logged in as horus.admin | 1. Go to /admin/metrics 2. Read the request-rate and latency panels 3. Cross-check with http://localhost:8000/metrics | Metrics are displayed for the running services and are consistent with the raw Prometheus endpoint.
F35 | Open the traces page and follow a request | Secondary function | Done | Mixed | 3 | 2 | 1 |  |  |  | Major | OK |  |  | OK |  |  | OK |  |  | Partial | Major | /admin/traces and opens them with a span waterfall and per-span things | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | Partial | Major | /admin/traces lists traces and opens them with a span waterfall and per-span timings (verified on an agent heartbeat trace: 18 spans across agent and mas-service). Not obtained: there is no trace for any chat request (no POST /tasks/new_task trace in 24 h, only DB spans, heartbeats and GETs), no trace shows RabbitMQ or knowledge-store hops, and the "mas" entry in the Service filter returns 0 traces because Tempo names the service "mas-service". | A request can be followed end to end across services | Logged in as horus.admin; at least one chat exchange completed | 1. Go to /admin/traces 2. Open a trace for a chat request 3. Expand the spans | The trace shows the hops across MAS, RabbitMQ, the agent and the knowledge store, with per-span timings.
F36 | Run the web client in different browsers | Compatibility | In progress | Mixed | 3 | 2 | 1 |  |  |  | Minor | OK |  |  | OK |  |  | OK |  |  | Partial | Minor | tested chrome 131 and firefox 133: login chat message wieh answer document upload and dashboard all bahave the same with no console erros | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | Partial | Minor | Tested Chrome 131 and Firefox 133: login, chat message with answer, document upload and dashboard all behave the same, with no console errors. In both browsers the layout overflows horizontally on the dashboard and knowledge store (see F37). Minor: in Chrome the Total Documents tile did not update immediately after an upload although the file was listed. | The web client behaves the same across the main browsers | Stack running | 1. Run F6, F17, F12 and F31 in Chrome 2. Repeat in Firefox 3. Repeat in a third browser for your platform: Windows Edge macOS Safari Linux Chromium (Edge is not required) | Login, chat, upload and dashboard behave identically in all three browsers tested, with no console errors and no broken layout. Record which third browser you used.
F37 | Use the interface on a small screen | Compatibility | In progress | Mixed | 3 |  | 3 |  |  |  | Major | OK |  |  | OK |  |  | OK |  |  | KO | Major | The page scrolls horizontally. Mesuared overflow | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | KO | Major | The page body scrolls horizontally. Measured overflow: /dashboard 171 px at 1366x768 and 769 px at 768 px width; /knowledge-store 364 px even at 1920x1080, 758 px at 1366x768 and 1356 px at 768 px. The header bar, the stat tiles and the Status column of the tables are cut off at the right edge. /chat has no overflow at any width. The sidebar navigation stays reachable at every width. | The interface stays usable on a smaller screen | Stack running | 1. Open the dashboard at 1920x1080 2. Resize to 1366x768, then to a tablet width 3. Check the navigation, the chat and the knowledge store | No horizontal scrolling of the page body, no overlapping elements, and the navigation stays reachable at every width.

## Findings
Feature ID | Feature Name | Category | Type | Tester | Result | Severity | Feedback / anomaly (verbatim) | Expected result
F25 | Create a task | Critical feature | Defect | Tester 4 | KO | Blocking | Crash and "something went wrong" | The task is accepted, given an id, and appears with status pending then running.
F25 | Create a task | Critical feature | Defect | Tester 6 | KO | Blocking | The /tasks/new page crashes before anything is submitted and shows the generic "Something went wrong" error page. Browser console shows: [@mantine/core] Duplicate options are not supported. Option with value "1_Q4_2025_Financial_Report.md" was provided more than once. Cause: the file-attachments picker on the page uses the document filename as the option key, and the knowledge store contained the same file twice (uploaded a second time during testing). The app should not crash when two documents share a filename. Task creation itself works: the same request sent to the backend API returns 200 and a task id. Workaround: delete one of the duplicate documents on /knowledge-store, after which the form renders and dispatches correctly. | The task is accepted, given an id, and appears with status pending then running.
F13 | Search the documents | Critical feature | Defect | Tester 1 | KO | Major | Didnt work - Simply nothing happened. Maybe I am blind but i didnt find the filters either. | Results come back in under 3 s, ranked, with a readable text excerpt per hit. The category filter removes non-Finance documents.
F13 | Search the documents | Critical feature | Defect | Tester 3 | KO | Major | Nothing happened, doesnt work | Results come back in under 3 s, ranked, with a readable text excerpt per hit. The category filter removes non-Finance documents.
F13 | Search the documents | Critical feature | Defect | Tester 4 | KO | Major | No result come back | Results come back in under 3 s, ranked, with a readable text excerpt per hit. The category filter removes non-Finance documents.
F13 | Search the documents | Critical feature | Defect | Tester 6 | KO | Major | No result come back | Results come back in under 3 s, ranked, with a readable text excerpt per hit. The category filter removes non-Finance documents.
F14 | List categories | Secondary function | Defect | Tester 1 | KO | Major | Did not find filtres. | The filter offers exactly the categories that were assigned to the uploaded documents, with no duplicates and no empty entries.
F14 | List categories | Secondary function | Defect | Tester 3 | KO | Major | The same, couldnt find the filters | The filter offers exactly the categories that were assigned to the uploaded documents, with no duplicates and no empty entries.
F14 | List categories | Secondary function | Defect | Tester 4 | KO | Major | No catecory filter | The filter offers exactly the categories that were assigned to the uploaded documents, with no duplicates and no empty entries.
F14 | List categories | Secondary function | Defect | Tester 6 | KO | Major | No category filter | The filter offers exactly the categories that were assigned to the uploaded documents, with no duplicates and no empty entries.
F15 | Delete a document | Critical feature | Defect | Tester 3 | KO | Major | Didnt worked the seaarch | Steps 1-4: the document leaves the list and the Total Documents counter drops by one. Steps 5-6: no excerpt from the deleted document is returned and the agent no longer cites it. No phantom results.
F19 | Ask a complex question spanning several documents | Critical feature | Defect | Tester 4 | KO | Major | Bad reponse | GPU REQUIRED - see Prerequisites. The answer arrives in under 60 s and cites BOTH 1_Q4_2025_Financial_Report.md and 4_Expense_Policy.md. It must show, in the answer text: the Q4 spend figures it used the matching threshold from the expense policy a stated conclusion on whether each item is within policy A bare yes or no, or an answer citing only one document, does not pass.
F20 | Ask a question outside the corpus | Critical feature | Defect | Tester 6 | KO | Major | Response for user : The capital of Peru is Lima. | GPU REQUIRED - see Prerequisites. The agent states that the knowledge base contains nothing relevant instead of presenting an ungrounded answer as fact.
F27 | Receive a task result without refreshing | Critical feature | Defect | Tester 1 | KO | Major | Task seems stuck. I waited ~10 minutes. | A task-result notification arrives over the WebSocket and the UI updates on its own; the payload matches the detail page.
F27 | Receive a task result without refreshing | Critical feature | Defect | Tester 3 | KO | Major | I had to wait more than 5 minutes, something is not rgiht there | A task-result notification arrives over the WebSocket and the UI updates on its own; the payload matches the detail page.
F28 | View the task list | Critical feature | Defect | Tester 4 | KO | Major | The tiles and the table not add up. total tasks ashowed 10 while the recent task table listed 8 | The submitted tasks are listed with their status. The six state tiles and the two totals add up: Total Tasks equals the number of tasks listed, and each tile matches the count of tasks in that state in the table.
F28 | View the task list | Critical feature | Defect | Tester 6 | KO | Major | The tiles and the table do not add up. Total Tasks showed 10 while the Recent tasks table listed 8. The Completed tile also counted 2 more than the table. Cause: the stats endpoint counts every task row including subtasks of decomposed tasks, while the list shows only root tasks. The two extra rows are the subtasks of the F19 multi-document question. | The submitted tasks are listed with their status. The six state tiles and the two totals add up: Total Tasks equals the number of tasks listed, and each tile matches the count of tasks in that state in the table.
F34 | Open the metrics page | Secondary function | Defect | Tester 1 | KO | Major | There are no latency panels. | Metrics are displayed for the running services and are consistent with the raw Prometheus endpoint.
F34 | Open the metrics page | Secondary function | Defect | Tester 3 | KO | Major | Couldnt find the latency panels | Metrics are displayed for the running services and are consistent with the raw Prometheus endpoint.
F37 | Use the interface on a small screen | Compatibility | Defect | Tester 4 | KO | Major | The page scrolls horizontally. Mesuared overflow | No horizontal scrolling of the page body, no overlapping elements, and the navigation stays reachable at every width.
F37 | Use the interface on a small screen | Compatibility | Defect | Tester 6 | KO | Major | The page body scrolls horizontally. Measured overflow: /dashboard 171 px at 1366x768 and 769 px at 768 px width; /knowledge-store 364 px even at 1920x1080, 758 px at 1366x768 and 1356 px at 768 px. The header bar, the stat tiles and the Status column of the tables are cut off at the right edge. /chat has no overflow at any width. The sidebar navigation stays reachable at every width. | No horizontal scrolling of the page body, no overlapping elements, and the navigation stays reachable at every width.
F35 | Open the traces page and follow a request | Secondary function | Defect | Tester 4 | Partial | Major | /admin/traces and opens them with a span waterfall and per-span things | The trace shows the hops across MAS, RabbitMQ, the agent and the knowledge store, with per-span timings.
F35 | Open the traces page and follow a request | Secondary function | Defect | Tester 6 | Partial | Major | /admin/traces lists traces and opens them with a span waterfall and per-span timings (verified on an agent heartbeat trace: 18 spans across agent and mas-service). Not obtained: there is no trace for any chat request (no POST /tasks/new_task trace in 24 h, only DB spans, heartbeats and GETs), no trace shows RabbitMQ or knowledge-store hops, and the "mas" entry in the Service filter returns 0 traces because Tempo names the service "mas-service". | The trace shows the hops across MAS, RabbitMQ, the agent and the knowledge store, with per-span timings.
F1 | Install and start Horus from the archive | Critical feature | Defect | Tester 5 | Partial | Minor | Install took more than 2 hours total (readme says 10-30 min). It failed 2 times with docker hub timeouts when pulling multiple images at same time (redis, rabbitmq etc), but pulling them one by one worked fine so i think its a parallel download issue not my network. After that, build finished ok but exit code 42 happened because 'mas' container was marked unhealthy - checked mas logs myself and everything was actually fine, no errors, i think the healthcheck just needs more time on first boot. Because of that the installer stopped before starting web_client and agent, so localhost:3000 didnt work at first. Had to manually run 'docker compose up -d' again to get the rest of the containers up. After that i could reach the login screen fine. | The installer runs its preflight checks (Python, Docker, Compose, free disk, network, ports), probes the hardware, chooses a profile, builds and starts the stack, and finishes with a 9-step smoke test. On failure it gives a distinct exit code and an actionable message, plus install-log.txt and horus-profile.json to send back. http://localhost:3000 shows the Horus login screen. With an NVIDIA GPU: 12 services are Up, 5 of them health-checked and healthy (mas, postgres, redis, rabbitmq, vllm). Without a GPU: the installer prints a warning up front, selects the CPU profile, and 11 services are Up with 4 healthy. The install still completes and reports success. Only F18, F19 and F20 are out of reach on a CPU install; record those as NOT APPLICABLE. vllm downloads its model last, so it is the last to go healthy. Allow extra time.
F7 | Log out | Secondary function | Defect | Tester 1 | Partial | Minor | Slight delay, if I click instant it restores an authenticated view, I managed to recreate it a couple of times. | The user returns to the login page and the back button does not restore an authenticated view.
F26 | Route a task to a matching agent | Critical feature | Defect | Tester 1 | Partial | Minor | I should not have to research for the login credentials. | The task is routed to FinCorp-Analyst and not to the unrelated agent; the queue shows the message on the matching route.
F29 | Open a task's detail view | User interface | Defect | Tester 6 | Partial | Minor | The detail page shows the demand, assigned agent, status and the result. Missing: the required skills are not displayed anywhere, and there are no created/finished timestamps (only the time on the Message Flow entry). Cosmetic: the agent card keeps showing a loading spinner after the task is completed. | The page shows the demand, required skills, assigned agent, status, timestamps and the result when the task has finished.
F30 | Cancel a task | Critical feature | Defect | Tester 1 | Partial | Minor | Took too long to load, closed my session. But ended up cancelling. | The task moves to Cancelled within 5 s, the Cancelled counter on /tasks increases by one, and no result is produced for it afterwards.
F36 | Run the web client in different browsers | Compatibility | Defect | Tester 4 | Partial | Minor | tested chrome 131 and firefox 133: login chat message wieh answer document upload and dashboard all bahave the same with no console erros | Login, chat, upload and dashboard behave identically in all three browsers tested, with no console errors and no broken layout. Record which third browser you used.
F36 | Run the web client in different browsers | Compatibility | Defect | Tester 6 | Partial | Minor | Tested Chrome 131 and Firefox 133: login, chat message with answer, document upload and dashboard all behave the same, with no console errors. In both browsers the layout overflows horizontally on the dashboard and knowledge store (see F37). Minor: in Chrome the Total Documents tile did not update immediately after an upload although the file was listed. | Login, chat, upload and dashboard behave identically in all three browsers tested, with no console errors and no broken layout. Record which third browser you used.
F13 | Search the documents | Critical feature | Defect | Tester 5 | KO |  | There is no search field inside the knowledge-store page itself, only the global nav search bar at top which just suggests pages to go to (Dashboard, Chat, Knowledge Store), it doesnt search inside documents at all. Also i dont see any category filter anywhere on this page, just a static table with Document/Category/Summary/Date/Size/Details columns. Tried clicking around (the icons next to the bell, the Category column header) but found nothing | Results come back in under 3 s, ranked, with a readable text excerpt per hit. The category filter removes non-Finance documents.
F14 | List categories | Secondary function | Defect | Tester 5 | KO |  | Cant test this because there is no category filter UI anywhere on the knowledge-store page (same issue as F13). The categories are only visible as plain text in the table column, no dropdown/filter to open and compare against. | The filter offers exactly the categories that were assigned to the uploaded documents, with no duplicates and no empty entries.
F27 | Receive a task result without refreshing | Critical feature | Defect | Tester 5 | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | A task-result notification arrives over the WebSocket and the UI updates on its own; the payload matches the detail page.
F28 | View the task list | Critical feature | Defect | Tester 5 | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | The submitted tasks are listed with their status. The six state tiles and the two totals add up: Total Tasks equals the number of tasks listed, and each tile matches the count of tasks in that state in the table.
F29 | Open a task's detail view | User interface | Defect | Tester 5 | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | The page shows the demand, required skills, assigned agent, status, timestamps and the result when the task has finished.
F30 | Cancel a task | Critical feature | Defect | Tester 5 | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | The task moves to Cancelled within 5 s, the Cancelled counter on /tasks increases by one, and no result is produced for it afterwards.
F31 | Access the dashboard | Critical feature | Defect | Tester 5 | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | The dashboard renders in under 3 s on each of the five reloads, with the agents list and the analytics widget, and no error state. The graph refreshes about every 10 s, and the active agents, running tasks and pending tasks series move when the new task is submitted.
F32 | Navigate with the command palette | User interface | Defect | Tester 5 | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | Each entry navigates to the matching page without a full page reload.
F33 | Open the logs page | Secondary function | Defect | Tester 5 | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | Recent log lines from the selected service are shown and reflect the actions performed during this test run.
F34 | Open the metrics page | Secondary function | Defect | Tester 5 | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | Metrics are displayed for the running services and are consistent with the raw Prometheus endpoint.
F35 | Open the traces page and follow a request | Secondary function | Defect | Tester 5 | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | The trace shows the hops across MAS, RabbitMQ, the agent and the knowledge store, with per-span timings.
F36 | Run the web client in different browsers | Compatibility | Defect | Tester 5 | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | Login, chat, upload and dashboard behave identically in all three browsers tested, with no console errors and no broken layout. Record which third browser you used.
F37 | Use the interface on a small screen | Compatibility | Defect | Tester 5 | KO |  | Cant continue testing, my pc froze/crashed while horus was running, its too heavy for my machine to keep going. And my machine isnt weak: Ryzen 7, 16GB RAM, NVIDIA RTX 4050, plenty of free disk space. If it struggles on this, i dont want to imagine trying to run it on a regular office pc, or worse, on 100 of them at once. 12 containers running at the same time plus the model in memory is just too much, computer becomes unusable, not just slow. Not testable on my hardware, stopping here. | No horizontal scrolling of the page body, no overlapping elements, and the navigation stays reachable at every width.
F7 | Log out | Secondary function | Defect | Tester 3 | Partial |  |  | The user returns to the login page and the back button does not restore an authenticated view.
F26 | Route a task to a matching agent | Critical feature | Defect | Tester 5 | Partial |  | My computer crashed/froze while i was testing this, right when i was about to submit the task. Not sure yet if it was something with horus itself using too much memory/cpu or just my pc being weak, need to check resource usage next time before retrying | The task is routed to FinCorp-Analyst and not to the unrelated agent; the queue shows the message on the matching route.
F29 | Open a task's detail view | User interface | Defect | Tester 4 | Partial |  | Skils are not there and the created /finished tiemestamps | The page shows the demand, required skills, assigned agent, status, timestamps and the result when the task has finished.
F30 | Cancel a task | Critical feature | Defect | Tester 2 | Partial |  |  | The task moves to Cancelled within 5 s, the Cancelled counter on /tasks increases by one, and no result is produced for it afterwards.
F13 | Search the documents | Critical feature | Blocked | Tester 2 | Blocked | Blocking | It never loads | Results come back in under 3 s, ranked, with a readable text excerpt per hit. The category filter removes non-Finance documents.
F14 | List categories | Secondary function | Blocked | Tester 2 | Blocked | Blocking | It never loads | The filter offers exactly the categories that were assigned to the uploaded documents, with no duplicates and no empty entries.
F15 | Delete a document | Critical feature | Blocked | Tester 1 | Blocked | Blocking | Search did not work previously. | Steps 1-4: the document leaves the list and the Total Documents counter drops by one. Steps 5-6: no excerpt from the deleted document is returned and the agent no longer cites it. No phantom results.
F26 | Route a task to a matching agent | Critical feature | Blocked | Tester 2 | Blocked |  | Cannot login I dont now the username | The task is routed to FinCorp-Analyst and not to the unrelated agent; the queue shows the message on the matching route.
F27 | Receive a task result without refreshing | Critical feature | Blocked | Tester 2 | Blocked |  | Never finishes | A task-result notification arrives over the WebSocket and the UI updates on its own; the payload matches the detail page.
F18 | Ask a question and receive a grounded answer | Critical feature | Note | Tester 1 | N/A |  | CPU Only | GPU REQUIRED - see Prerequisites. The answer arrives in under 15 s, identifies Q4 2025 revenue as $4.2M, and cites 1_Q4_2025_Financial_Report.md as its source. The figure may be returned on its own (for example '$4.2M'). That is acceptable as long as the source is named, either in the message or in the sources panel beside it. Answers are cached by exact question text, so a re-test needs different wording.
F18 | Ask a question and receive a grounded answer | Critical feature | Note | Tester 2 | N/A |  | We don't have a GPU | GPU REQUIRED - see Prerequisites. The answer arrives in under 15 s, identifies Q4 2025 revenue as $4.2M, and cites 1_Q4_2025_Financial_Report.md as its source. The figure may be returned on its own (for example '$4.2M'). That is acceptable as long as the source is named, either in the message or in the sources panel beside it. Answers are cached by exact question text, so a re-test needs different wording.
F19 | Ask a complex question spanning several documents | Critical feature | Note | Tester 1 | N/A |  | CPU Only | GPU REQUIRED - see Prerequisites. The answer arrives in under 60 s and cites BOTH 1_Q4_2025_Financial_Report.md and 4_Expense_Policy.md. It must show, in the answer text: the Q4 spend figures it used the matching threshold from the expense policy a stated conclusion on whether each item is within policy A bare yes or no, or an answer citing only one document, does not pass.
F19 | Ask a complex question spanning several documents | Critical feature | Note | Tester 2 | N/A |  | We don't have a GPU | GPU REQUIRED - see Prerequisites. The answer arrives in under 60 s and cites BOTH 1_Q4_2025_Financial_Report.md and 4_Expense_Policy.md. It must show, in the answer text: the Q4 spend figures it used the matching threshold from the expense policy a stated conclusion on whether each item is within policy A bare yes or no, or an answer citing only one document, does not pass.
F20 | Ask a question outside the corpus | Critical feature | Note | Tester 1 | N/A |  | CPU Only | GPU REQUIRED - see Prerequisites. The agent states that the knowledge base contains nothing relevant instead of presenting an ungrounded answer as fact.
F20 | Ask a question outside the corpus | Critical feature | Note | Tester 2 | N/A |  | We don't have a GPU | GPU REQUIRED - see Prerequisites. The agent states that the knowledge base contains nothing relevant instead of presenting an ungrounded answer as fact.
F1 | Install and start Horus from the archive | Critical feature | Note | Tester 1 | OK |  | I don't think that for a tester it should be installed that way and locally. It takes a lot of time, network bandwith, etc. To be completely honest, this kind of setup should NOT be done by the betatester, specially with the amount of resources required. A live demo in a VPS or similar should be provided. If it is helpful, here I provide the specs of my laptop: Host: TUXEDO InfinityBook Pro Gen8 (MK1) OS: Arch Linux x86_64 Kernel: 6.18.50-1-lts CPU: 13th Gen Intel Core i7-13700H, 20 threads, 3.5 GHz GPU: Intel Raptor Lake-P, Iris Xe Graphics Memory: 32 GB RAM | The installer runs its preflight checks (Python, Docker, Compose, free disk, network, ports), probes the hardware, chooses a profile, builds and starts the stack, and finishes with a 9-step smoke test. On failure it gives a distinct exit code and an actionable message, plus install-log.txt and horus-profile.json to send back. http://localhost:3000 shows the Horus login screen. With an NVIDIA GPU: 12 services are Up, 5 of them health-checked and healthy (mas, postgres, redis, rabbitmq, vllm). Without a GPU: the installer prints a warning up front, selects the CPU profile, and 11 services are Up with 4 healthy. The install still completes and reports success. Only F18, F19 and F20 are out of reach on a CPU install; record those as NOT APPLICABLE. vllm downloads its model last, so it is the last to go healthy. Allow extra time.
F11 | Unregister an agent | Critical feature | Note | Tester 1 | OK |  | UI needs improvement - A lot of horizontal scroll. | The agent disappears from the registry and no new task is routed to it. After step 5 it is back and routable.